## Calendar (EN)
Hotcoin · Marketing calendar · Oct 19 – Nov 15, 2026
Halloween theme Oct 19–31 · Ronaldinho global affiliate teasers Nov 1–4, reveal Nov 5 · all vouchers = futures trial vouchers (USD)
1 · Weekly plan by workstream
Workstream | Wk 1 · Oct 19–25 | Wk 2 · Oct 26 – Nov 1 | Wk 3 · Nov 2–8 | Wk 4 · Nov 9–15
Theme | 🎃 Spooky season starts (light: Halloween look on regular posts) | 🎃 Halloween peak · Oct 31 = Halloween + Bitcoin whitepaper 18 yrs | ⚽ Ronaldinho reveal week | ⚽ Ronaldinho follow-up · 11.11
Ronaldinho (global affiliate) | No official promo in October (per agency) | Nov 1 (Sun): teaser 1 of 5 | Nov 2–4: teasers 2–4 · Nov 5 (Thu): REVEAL — landing page post + media release + synced superstar social post | Sustain: official Brazil-shoot creatives only
X giveaways (3 / week) | 2 themed: Halloween "trick or trade" · earnings season 1 new users only | 2 themed: Fed day (Oct 28) · Halloween / whitepaper 1 new users only | 2 themed: Ronaldinho reveal (if in scope) · Diwali 1 new users only | 2 themed: 11.11 · market theme of the week 1 new users only
Paid ads | Spooky season campaign · Meta (main) · ChatGPT ads (test) · TG ads (explore) | Spooky season campaign peak · ends Oct 31 | Switch to Ronaldinho creatives from Nov 5 (after review) | Ronaldinho campaign
Discord | 6 daily events (tweet raids, message boost, platform interaction, 1 trade/week…) in Halloween style · 2 weekly games · live trading lesson | Same · Halloween finale event | Same · Ronaldinho reveal watch-party / quiz | Same
2 · Key dates
Date | Day | Event | What we do
Oct 19 | Mon | Halloween theme starts | Light Halloween look on all channels; launch spooky season ads
~Oct 21 | Wed | Tesla earnings (est.) — big-tech earnings season | TradFi / stock futures post
Oct 27–28 | Tue–Wed | FOMC · decision Oct 28, 2:00 PM ET | Keep Oct 28 market-first, not costume-first
~Oct 29 | Thu | Apple, Amazon earnings (est.) | TradFi post
Oct 31 | Sat | Halloween + Bitcoin whitepaper 18 yrs + end of Uptober | Peak Halloween day · no Ronaldinho reveal here
Nov 1 | Sun | Ronaldinho teaser 1 · Moonvember starts | Teaser video 1 of 5
Nov 2–4 | Mon–Wed | Ronaldinho teasers 2–4 | One teaser per day; Nov 3 = US midterms, no political takes
Nov 5 | Thu | Ronaldinho REVEAL | Landing page post + media release + synced superstar social post
Nov 6 | Fri | US October jobs report (usually 1st Friday) | Macro post
Nov 8 | Sun | Diwali (festival Nov 6–10) | Greeting post
Nov 11 | Wed | Singles' Day 11.11 | Promo post / giveaway theme
3 · Weekly voucher budget (USD, futures trial)
Item | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Total
X themed giveaways (2 × $100) | 200 | 200 | 200 | 200 | 800
X new-users giveaway (1 × $100) | 100 | 100 | 100 | 100 | 400
Discord 6-day programme (top 5 × $10) | 50 | 50 | 50 | 50 | 200
Discord games (DLS + eFootball, $10 each) | 20 | 20 | 20 | 20 | 80
Trading lesson with Mellst (max) | 70 | 70 | 70 | 70 | 280
Total | 440 | 440 | 440 | 440 | 1760
Blue numbers are inputs — edit them and totals update. Paid ads budget not included (TBD). Ronaldinho creatives: official Brazil shoot only, no AI spokesperson images; review via Siri.
Note on A28: From brief: 2 weekly themed giveaways, $100 each to 10 random winners
Note on A29: From brief: 1 weekly giveaway for new users only, $100
Note on A30: From Discord announcement: top 5 × $10
Note on A31: Assumes one winner per game per week
Note on A32: Range $45–70 per week; pending approval from Loris & Elena

## 日程 (中文)
Hotcoin · 营销日程 · 2026 年 10 月 19 日 – 11 月 15 日
万圣节主题 10/19–10/31 · 小罗全球代言预热 11/1–11/4，11/5 正式官宣 · 所有奖励均为合约体验金（美元）
1 · 各板块周计划
板块 | 第 1 周 · 10/19–10/25 | 第 2 周 · 10/26–11/1 | 第 3 周 · 11/2–11/8 | 第 4 周 · 11/9–11/15
主题 | 🎃 万圣节季开始（轻度：常规内容加入万圣节元素） | 🎃 万圣节高峰 · 10/31 = 万圣节 + 比特币白皮书 18 周年 | ⚽ 小罗官宣周 | ⚽ 小罗持续推广 · 双十一
小罗（全球代言） | 10 月无官方大规模推广（代理商要求） | 11/1（周日）：预热视频 1/5 | 11/2–11/4：预热 2–4 · 11/5（周四）：正式官宣 —— 落地页帖子 + 媒体新闻稿 + 球星社媒同步发布 | 持续推广：仅使用巴西官方拍摄素材
X 抽奖（每周 3 场） | 2 场主题：万圣节"不交易就捣蛋" · 财报季 1 场仅限新用户 | 2 场主题：美联储议息日（10/28）· 万圣节 / 白皮书 1 场仅限新用户 | 2 场主题：小罗官宣（如授权允许）· 排灯节 1 场仅限新用户 | 2 场主题：双十一 · 本周市场热点 1 场仅限新用户
付费广告 | 万圣节季广告 · Meta（主力）· ChatGPT 广告（测试）· TG 广告（探索） | 万圣节广告高峰 · 10/31 结束 | 11/5 起切换为小罗素材（审核后） | 小罗广告投放
Discord | 6 项每日活动（推特冲榜、消息互动、平台互动、每周一笔交易等）万圣节风格 · 每周 2 场游戏 · 直播交易课堂 | 同上 · 万圣节压轴活动 | 同上 · 小罗官宣观看派对 / 竞猜 | 同上
2 · 关键日期
日期 | 星期 | 事件 | 我们的动作
10/19 | 周一 | 万圣节主题开始 | 全渠道加入轻度万圣节元素；上线万圣节广告
约 10/21 | 周三 | 特斯拉财报（预计）· 科技股财报季 | TradFi / 美股合约内容
10/27–10/28 | 周二–周三 | 美联储议息会议 · 10/28 美东 14:00 公布 | 10/28 以市场内容为主，弱化万圣节
约 10/29 | 周四 | 苹果、亚马逊财报（预计） | TradFi 内容
10/31 | 周六 | 万圣节 + 比特币白皮书 18 周年 + Uptober 收官 | 万圣节高峰日 · 不在当天官宣小罗
11/1 | 周日 | 小罗预热 1 · Moonvember 开始 | 预热视频 1/5
11/2–11/4 | 周一–周三 | 小罗预热 2–4 | 每天一条预热；11/3 美国中期选举，不发表政治观点
11/5 | 周四 | 小罗正式官宣 | 落地页帖子 + 媒体新闻稿 + 球星社媒同步发布
11/6 | 周五 | 美国 10 月非农就业数据（通常为首个周五） | 宏观内容
11/8 | 周日 | 排灯节（节期 11/6–11/10） | 节日祝福帖
11/11 | 周三 | 双十一 | 促销帖 / 抽奖主题
3 · 每周体验金预算（美元，合约体验金）
项目 | 第 1 周 | 第 2 周 | 第 3 周 | 第 4 周 | 合计
X 主题抽奖（2 × $100） | 200 | 200 | 200 | 200 | 800
X 新用户抽奖（1 × $100） | 100 | 100 | 100 | 100 | 400
Discord 六日活动（前 5 名 × $10） | 50 | 50 | 50 | 50 | 200
Discord 游戏（DLS + eFootball，各 $10） | 20 | 20 | 20 | 20 | 80
Mellst 交易课堂（上限） | 70 | 70 | 70 | 70 | 280
合计 | 440 | 440 | 440 | 440 | 1760
蓝色数字为输入项，修改后合计自动更新。未含付费广告预算（待定）。小罗素材：仅用巴西官方拍摄素材，不使用 AI 生成的代言人形象；需经 Siri 审核。
Note on A28: 来源：每周 2 场主题抽奖，每场 $100 分给 10 位随机用户
Note on A29: 来源：每周 1 场仅限新用户抽奖，$100
Note on A30: 来源：Discord 公告，前 5 名各 $10
Note on A31: 假设每个游戏每周 1 位冠军
Note on A32: 每周 $45–70；待 Loris 与 Elena 审批